SOX Evidence | Control SAP.MC1 | CHARM Ticket 800098354729
Normal Change | ERP Version Change | Developer: Amy Singh | Change Mgr: Neha Sharma
NORMAL CHANGE 800098354729 — SAP Solution Manager (CHARM)
1
2
3
4
5
6
7
8
Created
In Dev
Tested
Biz
Tech
Appr
Import
Doc
Appr
Appr
Prod
Prod
General Data
ID:
800098354729
Status:
Imported to Production
Description:
ERP version change
Priority:
4: Low
PASS
TS-1 · Documentation
Change Request formally documented
Developer:
Amy Singh
Creation Date:
19.09.2025
in CHARM prior to work initiation.
Tester:
Sofia Khan
Last Changed:
29.09.2025
ID: 800098354729
Created: 19.09.2025 by Amy Singh
Change Manager:
Neha Sharma
Change Cycle:
Build / XXX_PDC
'In Development' set 19.09.2025
Current Processor:
Due By:
07.10.2025
WP Ref: SAP-MC1_S1 | Control: SAP.MC1 | SOX Evidence | 23 Apr 2026
Page 1 of 3

---
SOX Evidence | Control SAP.MC1 | CHARM 800098354729 | Actions & Approvals
Scheduled Actions Log | Text Log | All approvals sequencing verified
Scheduled Actions Log — CHARM 800098354729
Action
Processor / Approver
Date
Status
During Creation
Processed
Set to 'In Development'
Processed
Successfully Tested
25.09.2025
Processed
Business Approved (QA)
Kamal Rajaram
28.09.2025
Processed
Tech Approved
David Harry
30.09.2025
Processed
Approved for Production
Vivek Verma
02.10.2025
Processed
06.10.2025
Processed
Text Log — CHARM 800098354729
06.10.2025 Neha Sharma:
  The status was set to the value 'Imported to Production'
02.10.2025 Vivek Verma:
  The status was set to the value 'Approved for Production'
30.09.2025 David Harry:
  The status was set to value E0018 (Tech Approved (QA))
28.09.2025 Kamal Rajaram:
TS-2 · Testing & Approval
'Successfully Tested'
TS-3a · Technology Approval
TS-3b · Business Approval
  Tester: Sofia Khan — 25.09.2025
Tech Approved: David Harry
Business Approved: Kamal Rajaram
'Business Approved (QA)'
  Date: 30.09.2025
  Date: 28.09.2025
  Approver: Kamal Rajaram — 28.09.2025
Text Log: E0018 (Tech Approved (QA))
Text Log 28.09 corroborates.
Text Log 28.09 independently
David Harry confirmed on
Kamal Rajaram confirmed on
corroborates. Stages 3 & 4
  Authorized Approver List.
  Authorized Approver List.
confirmed complete before
30.09 precedes 02.10 & 06.10.
28.09 precedes all subsequent.
Tech Approval (30.09.2025).
Page 2 of 3

---
SOX Test Results Summary | Control SAP.MC1 | Sample S-001
CHARM 800098354729 | WP Ref: SAP-MC1_S1 | Overall Conclusion
SOX TEST RESULTS SUMMARY · SAP.MC1 · Sample S-001 · CHARM 800098354729
Control: Change Management — System & Application Testing and Approval Prior to Production Promotion
Documentation
Change request formally documented in CHARM (ticket 800098354729)
created 19.09.2025 by Amy Singh. 'In Development' set same day.
TS-1
Precedes implementation date (06.10.2025) by 17 days.
Documentation
Conf: 99%
WP Ref: SAP-MC1_S1 | CHARM ticket General Data
Testing & QA Approval
'Successfully Tested' — Sofia Khan — 25.09.2025.
'Business Approved (QA)' — Kamal Rajaram — 28.09.2025.
TS-2
Text Log 28.09.2025 independently corroborates. Stages 3 & 4 complete.
Testing
Conf: 97%
WP Ref: SAP-MC1_S1 | CHARM Scheduled Actions + Text Log
Technology Approval
'Tech Approved' — David Harry — 30.09.2025.
Text Log: E0018 (Tech Approved (QA)). David Harry on Authorized List.
TS-3a
30.09 precedes Production Approval (02.10) and Import (06.10).
Technology
Conf: 98%
WP Ref: SAP-MC1_S1 | CHARM Actions + Authorized Approver List
Business Approval
'Business Approved (QA)' — Kamal Rajaram — 28.09.2025.
Text Log corroborates. Kamal Rajaram on Authorized Approver List.
TS-3b
28.09 precedes Tech Approval (30.09) and Import (06.10).
Business
Conf: 98%
WP Ref: SAP-MC1_S1 | CHARM Actions + Authorized Approver List
Rel. Mgr Approval & Sequencing
'Approved for Production' — Vivek Verma — 02.10.2025.
REPERFORMANCE: SAP TMS Import — Neha Sharma — 06.10.2025.
TS-3c
→
→
→
Sequence: Biz(28.09)
Tech(30.09)
RelMgr(02.10)
Import(06.10). No bypass.
Rel.
Conf: 99%
WP Ref: SAP-MC1_S1 | CHARM Text Log + SAP TMS Import Log
OBSERVATIONS (Non-Exception)
No exceptions identified.
No observations for this sample.
All approvals by distinct,
authorized individuals.
OVERALL CONCLUSION · All 5 Test Steps PASS · Weighted Avg Confidence: ~98%
EFFECTIVE
No Exceptions Identified | Sampling Note: 1 sample — full population testing (25+) required for complete SOX period conclusion.
Auditor: SOX Testing Team | Date: 23 Apr 2026 | WP Ref: SAP-MC1_S1
Page 3 of 3